##### 课题名称

Decoding the Universe's Hidden Distortions: A Machine Learning Approach to Compress Astrophysical Systematics in Weak Lensing
宇宙隐藏扭曲的解码：压缩弱引力透镜中天体物理系统误差的机器学习方法

##### 课题介绍（需要在简介中明确课题解决的问题，研究意义以及预计研究成果）

English
Weak gravitational lensing is one of the key observational probes for mapping the large-scale distribution of matter and constraining cosmological parameters. However, its interpretation is affected by astrophysical systematics, especially intrinsic alignment, where galaxy shapes can become correlated through local gravitational and formation environments rather than lensing alone. If these additional correlations are not modelled properly, they may bias future weak-lensing measurements from surveys such as Euclid, Rubin Observatory LSST, and the Roman Space Telescope. This project investigates whether machine-learning methods can provide a compact representation of intrinsic-alignment two-point statistics. Instead of directly analysing high-dimensional theoretical power spectra, the project will train and evaluate dimensionality-reduction and generative models, such as PCA, autoencoders, and variational autoencoders, to compress these spectra into a small latent space while preserving their main physical dependence on cosmological and astrophysical parameters. The expected outcomes include a reproducible computational workflow, baseline compression models, quantitative reconstruction tests, latent-space interpretation, and a LaTeX research manuscript.

中文
弱引力透镜是研究宇宙大尺度物质分布并限制宇宙学参数的重要观测手段，但其解释会受到天体物理系统效应的影响。其中，内在对齐是一个关键例子：星系形状可能由于局部引力场和形成环境而产生相关性，而并非完全由引力透镜效应造成。如果这类额外相关信号没有被准确建模，未来的Euclid、Rubin Observatory LSST、Roman Space Telescope等巡天项目中的弱引力透镜测量可能会产生系统性偏差。本课题将探索机器学习方法能否为内在对齐两点统计提供一种更紧凑的表示方式。项目不会直接处理高维理论功率谱，而是训练并评估PCA、自编码器和变分自编码器等降维/生成模型，将功率谱压缩到少量潜在变量中，同时尽量保留其与宇宙学参数和天体物理参数相关的主要物理信息。预期成果包括可复现的计算流程、基线压缩模型、重构误差评估、潜变量空间解释，以及一篇LaTeX科研论文初稿。

##### 课题要求（课前需要掌握的基础知识与工具）

| 天文与宇宙学基础 | 宇宙学概论 | 弱引力透镜 | 内在对齐 |
| --- | --- | --- | --- |
| 计算与数据分析 | Python | NumPy / Matplotlib | Jupyter Notebook |
| 机器学习基础 | PCA | Autoencoder / VAE | 模型评估 |
| 学术写作 | LaTeX | 文献检索 | 科研图表 |
| 其他 | 英文摘要写作 |  |  |

##### 预期研究成果（根据课题设计及研究内容、研究方案说明研究的预期成果）

1. 建立intrinsic-alignment two-point statistics / power spectra的数据生成、读取、预处理与可视化流程。

2. 实现并比较PCA、autoencoder、variational autoencoder等低维压缩模型，评估latent dimension对重构质量的影响。

3. 分析latent variables与cosmological / astrophysical parameters之间的关系，判断压缩表示是否保留主要物理信息。

4. 完成可复现的Jupyter Notebook、主要科研图表、LaTeX论文初稿与项目展示材料。

##### 课题创新点（2-3条，说明研究内容、拟采用研究方法、技术路线或预期成果中有哪些创新之处）

1. 本课题将弱引力透镜中的天体物理系统误差建模转化为低维潜在表示学习问题，区别于直接在高维理论功率谱空间中进行建模。

2. 项目采用conditional generative compression的思路，将宇宙学/天体物理参数与功率谱压缩结合起来，探索latent space是否能够捕捉主要物理变化。

3. 预期结果可为未来Euclid、Rubin、Roman等巡天中的系统误差快速表示、模型比较和不确定性压缩提供概念验证。

##### 实验要求（如有）

本项目为计算型研究，无湿实验耗材需求。建议使用个人电脑或云端Notebook环境，安装Python 3、Jupyter Notebook、NumPy、SciPy、Matplotlib、scikit-learn、PyTorch或TensorFlow/Keras，以及LaTeX/Overleaf。GPU并非必须；若使用小型模拟数据，普通笔记本即可完成。预计额外成本为0；如使用云端GPU或付费计算平台，可根据实际训练规模预留约0-50美元。

##### 研究计划（有了具体学生再具体填写即可）

项目推进过程中，研究进度可以根据学生实际情况调整，如果学生研究进度不达预期，需要及时和有方工作人员联系。请务必每次课布置作业，随着课程的进行，按照下列计划模板进度布置论文撰写任务，按时完成论文初稿。

| Class | Content, Readings, Assignment |
| --- | --- |
| Class 1 | Topic: Cosmology background Content: 1. Big Bang and cosmic expansion 2. Dark matter/dark energy 3. Large-scale structure Readings: NASA/ESA outreach materials on cosmology; selected project slides. Assignment: Write a 300-word summary of why cosmology needs observational probes. |
| Class 2 | Topic: Weak lensing and intrinsic alignment Content: 1. Strong vs weak lensing 2. Galaxy-shape distortion 3. Intrinsic alignment as a systematic Readings: Bartelmann & Schneider, Weak Gravitational Lensing; Troxel & Ishak, Intrinsic Alignments review (selected sections). Assignment: Draw a concept diagram linking lensing, galaxy shapes, and IA contamination. |
| Class 3 | Topic: From science question to ML task Content: 1. IA power spectra as high-dimensional vectors 2. Compression objective 3. Reconstruction vs physical information Readings: Project abstract; Chollet, Deep Learning with Python, Ch. 1-2 (selected). Assignment: Draft research question, hypothesis, and expected outputs. |
| Class 4 | Topic: Power spectra and toy data Content: 1. Multipole/scale intuition 2. Parameter-dependent curves 3. Toy spectra generation Readings: Introductory notes on power spectra and two-point statistics. Assignment: Generate and plot toy spectra; start literature-review notes. |
| Phase I Evaluation 阶段性考察Embark 学生提交材料：Research Proposal；Manuscript draft (literature review, research question, hypothesis) |  |
| Class 5 | Topic: Python workflow and preprocessing Content: 1. NumPy arrays and shapes 2. Train/validation/test split 3. Normalisation/log scaling Readings: Chollet, Deep Learning with Python, Ch. 2 and Ch. 4 (selected). Assignment: Build a preprocessing notebook for toy or provided spectra. |
| Class 6 | Topic: PCA baseline Content: 1. Dimensionality reduction 2. Explained variance 3. PCA reconstruction error Readings: Scikit-learn PCA documentation; short PCA tutorial. Assignment: Apply PCA with different component numbers and plot reconstruction residuals. |
| Class 7 | Topic: Autoencoder compression Content: 1. Encoder/latent/decoder 2. Reconstruction loss 3. Latent dimension selection Readings: Chollet, Deep Learning with Python, neural-network and autoencoder notes. Assignment: Train a simple autoencoder and compare it with PCA. |
| Class 8 | Topic: Model evaluation Content: 1. Loss curves 2. Overfitting/underfitting 3. Error metrics for spectra Readings: Chollet, Deep Learning with Python, Ch. 4 (selected). Assignment: Prepare Methods draft: data, preprocessing, PCA, autoencoder setup. |
| Phase II Evaluation 阶段性考察Embark 学生提交材料：Manuscript draft (Research method: data generation/cleaning/processing, modelling plan, evaluation metrics) |  |
| Class 9 | Topic: Conditional compression Content: 1. Cosmological parameters 2. Astrophysical parameters 3. Conditioning strategy Readings: Project slide on conditional generative compression; selected IA modelling notes. Assignment: Design a conditional model diagram and update the methods section. |
| Class 10 | Topic: Variational autoencoder concept Content: 1. Latent distribution 2. Sampling 3. Reconstruction term and KL regularisation Readings: Kingma & Welling, Auto-Encoding Variational Bayes (conceptual overview); Chollet Ch. 8 (selected). Assignment: Implement or review a simplified VAE pipeline. |
| Class 11 | Topic: Physical interpretation of latent space Content: 1. Latent variables vs parameters 2. Sensitivity plots 3. Information preservation Readings: Selected examples of interpretable scientific ML. Assignment: Plot latent variables against input parameters and write preliminary observations. |
| Class 12 | Topic: Main IA-spectra experiment Content: 1. Train final baselines 2. Compare PCA/AE/VAE 3. Select key figures Readings: Review previous notes and project slides. Assignment: Produce final result figures: spectra, residuals, error table, latent-space plot. |
| Phase III Evaluation 阶段性考察Embark 学生提交材料：Manuscript draft (Pre-Result: data analysis, preliminary figures, conclusion outline) |  |
| Class 13 | Topic: Results and discussion Content: 1. Interpret reconstruction quality 2. Discuss model limits 3. Connect to future surveys Readings: Example astronomy/ML paper structure. Assignment: Draft Results and Discussion sections in LaTeX. |
| Class 14 | Topic: Manuscript finalisation Content: 1. Abstract/Introduction revision 2. Figure captions 3. Citation and LaTeX formatting Readings: Selected MNRAS/AAS paper-writing guidance. Assignment: Submit a complete manuscript draft for feedback. |
| Class 15 | Topic: Final presentation and revision Content: 1. Final paper polish 2. Presentation storyline 3. Q&A preparation Readings: Review all project materials. Assignment: Submit final paper, slides, and presentation script. |
| Final Evaluation 结项评审Embark或Research scientist 学生提交材料：Research paper, Self-reflection form 建议准备材料：PPT Slides, presentation script, reproducible notebook |  |